## Product Backlog
| PRODUCT BACKLOG | Overall sum of story points: | 129 |  |  | DoD1: Unit testing passed (75% code coverage) Functional testing (based on ACs) passed Usability testing passed (Safari v18.6+) Regression testing passed Approved by Product Owner
ID | USER STORY | OWNER | PRIORITY | EFFORT in story points | STATUS | DEFINITION OF DONE | NOTES
2 | As a customer, I want to be able to update all my account information such address, phone number and payment for easy checkout | Product Owner | Critical | 8 | To Do | DoD1 | Would help in smoother checkout process, better experience for customers
4 | As a staff, I want to add newly produced scarves, so that customers can purchase new scarves | Product Owner | Critical | 8 | To Do | DoD1 | Need to be done as soon as possible, it is part of the "Our Scarves" page, so customers would know if there are stock available
5 | As a customer, I want to know if a scarve is out of stock, so that I can check or purchases other scarves | Product Owner | High | 5 | To Do | DoD1 | Shopping cart with item management essentially, must be implemented after critical tasks
6 | As a user, I want to see my 'cart' page, so that I can check or remove items before proceeding to payment | Product Owner | Critical | 8 | To Do | DoD1 | Need for login page UI and functionality
7 | As a logged-out customer, I want to be able to to see the log-in page, so that I can log back in to my Victoria Scarves' account | Product Owner | High | 5 | To Do | DoD1 | Order history display functionality
10 | As a staff, I want to be able to update the stock of the scarves, so that customers could see the stock of our scarves | Product Owner | Critical | 8 | To Do | DoD1 | Important funtionality, business wants to see this implemented asap(according to stakeholder notes)
13 | As a customer, I want to receive a confirmation, so that I know if I have purchased a scarve | Product Owner | Medium | 3 | To Do | DoD1 | Confirmation through email once payment is processed, required before marking orders as delivered or picked up
21 | As a customer, I want to view all scarves (size and availability), so that I can decide what to buy | Product Owner | Critical | 8 | To Do | DoD1 | Core funtionality, should be implemented first
22 | As a customer, I want to add/remove scarves to/from my cart and update quantities, so that I can manage my purchases | Product Owner | Critical | 8 | To Do | DoD1 | Works without login. Must disable “Add” function for item out-of-stock
23 | As a customer, I want to choose my delivery option (pickup/Auspost/standard/express), so that I can receive my order conveniently | Product Owner | Critical | 5 | To Do | DoD1 | Delivery fee calculated by weight
24 | As a customer, I want to register an account with name, email, and password, so that I can purchase items | Product Owner | Critical | 5 | To Do | DoD1 | Password rules: ≥8 chars, ≥2 digits and 1 special character
25 | As a customer, I want to log in, so that I can access my account and checkout | Product Owner | Critical | 3 | To Do | DoD1 | Required before enabling payments
26 | As a customer, I want to pay via credit card or PayPal, so that I can complete my purchase online | Product Owner | Critical | 8 | To Do | DoD1 | Confirmation screen and email receipt
27 | As a customer, I want to receive a confirmation email of my purchase details, so that I have a record of my order | Product Owner | High | 5 | To Do | DoD1 | Includes items, prices, quantities, delivery method and total
28 | As a customer, I want to recover my password, so that I can regain access if I forget it | Product Owner | Medium | 3 | To Do | DoD1 | Standard functionality, can be later in project
29 | As a customer, I want to see the “Our Story” page, so that I can learn about the brand | Product Owner | Medium | 2 | To Do | DoD1 | Content/photos provided later
30 | As a customer, I want to see my account details and update them, so that my information is current | Product Owner | Medium | 5 | To Do | DoD1 | To be implemented in later sprints
31 | As a customer, I want to see my order history, so that I can track my past purchases | Product Owner | Low | 5 | To Do | DoD1 | Nice-to-have functionality
32 | As a customer, I want to add scarves to a wish list, so that I can save items for later | Product Owner | Low | 8 | To Do | DoD1 | Nice-to-have functionality
33 | As a staff member, I want to log in, so that I can access staff features | Product Owner | High | 3 | To Do | DoD1 | Must be before orders page
34 | As a staff member, I want to see all current orders in order of creation, so that I can prepare and mark them as fulfilled | Product Owner | High | 8 | To Do | DoD1 | Business prefers this in 2nd half of project
35 | As a staff manager, I want to add or revoke staff accounts, so that I can control staff access | Product Owner | Low | 8 | To Do | DoD1 | Implement only if time allows

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #REF!
| Previous Year | #REF! | #REF!
| Position | #REF! | #REF! | #REF! | #REF! | #REF!
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | As a customer, I want to know if a scarve is out of stock, so that I can check or purchases other scarves | #N/A | #N/A | #N/A | #N/A | #N/A
6 | As a user, I want to see my 'cart' page, so that I can check or remove items before proceeding to payment | #N/A | #N/A | #N/A | #N/A | #N/A
7 | As a logged-out customer, I want to be able to to see the log-in page, so that I can log back in to my Victoria Scarves' account | #N/A | #N/A | #N/A | #N/A | #N/A
8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | As a staff, I want to be able to update the stock of the scarves, so that customers could see the stock of our scarves | #N/A | #N/A | #N/A | #N/A | #N/A
11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | As a customer, I want to receive a confirmation, so that I know if I have purchased a scarve | #N/A | #N/A | #N/A | #N/A | #N/A
14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
19 | As a staff, I want to add newly produced scarves, so that customers can purchase new scarves | #N/A | #N/A | #N/A | #N/A | #N/A
20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
21 | As a customer, I want to view all scarves (size and availability), so that I can decide what to buy | #N/A | #N/A | #N/A | #N/A | #N/A
22 | As a customer, I want to add/remove scarves to/from my cart and update quantities, so that I can manage my purchases | #N/A | #N/A | #N/A | #N/A | #N/A
23 | As a customer, I want to choose my delivery option (pickup/Auspost/standard/express), so that I can receive my order conveniently | #N/A | #N/A | #N/A | #N/A | #N/A
24 | As a customer, I want to register an account with name, email, and password, so that I can purchase items | #N/A | #N/A | #N/A | #N/A | #N/A
25 | As a customer, I want to log in, so that I can access my account and checkout | #N/A | #N/A | #N/A | #N/A | #N/A